## Sheet1
| S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Performance Constraints
Performance matching plot | bar: M 1 to T 2
Pick design point | bar: W 3
Configuration Selection
Choice of overall config | bar: W 3; W 10 to R 11; W 17; W 24; W 3; W 10
Choose fuselage configuration | bar: W 3; W 10; W 17; W 24; W 3; W 10
Consider propulsion installation | bar: W 3; W 10 to M 15; W 17; W 24; W 3; W 10
Fuselage Layout
Develop overall fuselage layout | bar: T 9 to W 10
Cargo hold and cabin layout | bar: R 11
Cockpit layout | bar: F 12 to S 14
Structural layout | bar: M 15 to W 17
CAD model | bar: W 10 to F 19
Wing and Empennage
Get wing area from perf constraints | bar: W 3; W 10; W 17; W 24; W 3; W 10
Clean wing design/analysis | bar: W 10 to S 13
High lift layout | bar: S 14 to T 16
Layout of empennage | bar: W 17 to F 19
CAD Model | bar: M 15 to M 22
Propulsion
Req. thrust from perf constr | bar: W 3; W 10; W 17; W 24; W 3; W 10
Find suitable engines (3-4) | bar: W 3 to F 12; W 17; W 24; W 3; W 10
Decide on propulsion install | bar: W 3; W 10 to M 15; W 17; W 24; W 3; W 10
Check FOD / Clearance Rqmt | bar: W 3; W 10; S 14 to W 17; W 24; W 3; W 10
CAD Model | bar: W 3; W 10; F 12 to W 17; W 24; W 3; W 10
Weight & Balance
Class I weight breakdown | bar: M 8 to W 10
Balance & c.g. excursion | bar: R 11 to F 12
V-n Diagram | bar: S 13 to S 14
Class II weight predictions | bar: M 15 to R 18
Balance & c.g. excursion | bar: F 19 to S 21
Moments/Products of inertia | bar: M 22
Landing Gear
Wheel loads and tire sizing | bar: W 3; W 10 to S 14; W 17; W 24; W 3; W 10
Strut sizing | bar: W 3; W 10; M 15 to W 17; W 24; W 3; W 10
Disposition and geometry | bar: W 3; W 10; W 17 to F 19; W 24; W 3; W 10
Retraction kinematics | bar: W 3; W 10; W 17; S 20 to M 22; W 24; W 3; W 10
Compliance w/ tipover, FOD criteria | bar: W 3; W 10; W 17; T 23 to W 24; W 3; W 10
CAD Model | bar: W 3; W 10; W 17; F 19 to W 24; W 3; W 10
Drag
Wing | bar: M 8 to W 10
Empennage (h. and v. tail) | bar: R 11 to S 13
Fuselage | bar: S 14 to M 15
Nacelle/Pylon | bar: T 16 to W 17
Trim | bar: R 18 to S 20
Flap | bar: S 21 to M 22
Landing Gear | bar: T 23 to W 24
Induced Drag | bar: R 25 to M 1
Compressibility | bar: T 2 to W 3
Drag Polar | bar: S 21 to W 3
Systems Design
Flight Control System
Primary | bar: W 17 to F 19
Secondary | bar: R 18 to S 20
Fuel Control System | bar: S 21 to M 22
Electrical & Avionics System | bar: T 23 to W 24
Anti/De-icing System | bar: R 25 to F 26
Hydraulic System | bar: S 27
Water & Waste Systems | bar: S 28
CAD model of systems layout | bar: F 19 to T 2
Conflict Analysis | bar: S 28 to W 3
Stability and Control
Determination of a.c. | bar: W 24 to R 25
Trim diagrams | bar: F 26 to S 27
Takeoff rotation analysis | bar: S 28
Longitudinal stability derivatives | bar: M 1 to W 3
Longitudinal control derivatives | bar: R 4
Lat-Dir stability derivatives | bar: F 5 to S 7
Lat-Dir control derivatives | bar: M 8
OEI control | bar: T 9 to W 10
Flying/Handling qualities check | bar: W 3; W 10; W 17; W 24; W 3; W 10
Iterate on design | bar: W 3; W 10; W 17; W 24; W 3; W 10
Performance Analysis
Installed thrust | bar: W 24 to R 25
Installed fuel consumption | bar: F 26 to S 27
Specific range | bar: S 28 to M 1
Payload-range | bar: T 2 to W 3
Takeoff and landing distances | bar: R 4
Climb & dirftdown performance | bar: F 5 to S 6
Cost Analysis
RDTE cost | bar: W 24 to F 26
Manufacturing Cost | bar: S 27 to M 1
Prediction of AMP & AEP | bar: T 2 to W 3
Prediction of DOC | bar: R 4 to S 6
Prediction of IOC | bar: S 7 to M 8
Life Cycle Cost | bar: T 9 to W 10